## 1.Progress of ABSS Master Plans
PCDO for the Month of : April 2025
1. Progress of ABSS Master Plans
S.No | Name of Station | Division | Date of Master plan approval | TDC for approval of Master Plan | Total plot area (In Sqm.) | FAR applicable | Station built up Area (In Sqm.) *1 | Built up area marked for Comm. Dev. *2 (In Sqm.) | Remarks
1 | Talegaon | PA | 2024-01-11 |  | 22522.83
2 | Dehu Road |  | 2024-01-11 |  | 19498.9
3 | Akurdi |  | 2024-01-11 |  | 22151.54
4 | Chinchwad |  | 2024-06-02 |  | 20000
5 | Hadapsar |  | 2023-04-17 |  | 20000.32
6 | Uruli |  | 2024-06-02 |  | 20336.73
7 | Kedgaon |  | 2024-06-02 |  | 20609.93
8 | Baramati |  | 2024-06-02 |  | 25819.61
9 | Lonand |  | 2024-06-02 |  | 19442.9
10 | Wathar |  | 2024-06-02 |  | 13455.02
11 | Satara |  | 2024-06-02 |  | 26103.36
12 | Karad |  | 2024-06-02 |  | 17251.73
13 | Sangli |  | 2024-06-02 |  | 21894.9
14 | Hathkalangale |  | 2024-06-02 |  | 25384.98
15 | Kolhapur |  | 2024-06-02 |  | 24597.14
16 | Phaltan |  | Not required due to very small work |  | 1000
17 | Kopergaon |  | 2023-09-15 |  | 27300
18 | Belapur |  | 2023-07-25 |  | 10000
19 | Ahmednagar |  | 2023-07-25 |  | 26650
20 | Daund |  | 2023-07-25 |  | 18000
Total
*1 Station built-up area after phase 1
*2 Envisaged Commercial built-up area as per final phases of approved masterplan.
Note:- | Master Plan is being reviewed and verified in field for land boundry and other technical details along with the incorporation of 3rd & 4th line in PA-LNL section and doubling works in PA-MRJ section.
CPM/GSU/PA
CAO(C)RSP-CR

## 2.Progress of Phase I ABSS.
PCDO for the Month of April-2025
2. Progress of Phase I works of ABSS
Sr. No. | Name of Station | Division | Total sanction Cost of works planned in Phase-I (Cr.) | Sanction of Estimate for Phase-l | Scope of works for Phase I works | Status of Contracts for Phase-1 works | Executing Agency (Con./Div./GSU /RLDA) | Physical Prog. (%) (excluding FOB, ramp, Lift, Escalator) | Overall Physical Prog. (%) | Financial. Prog. (%) | Status | TDC
1 | Talegaon | PA | 40.34 | Yes | Facade, Portico, Circulating Area, COP & PF Surface, Toilet Block, Renovation works, Compound wall, Incorporating the local art and culture, Seating Facilities, Divyangjan Facilities, Illumination, Signage, Foot Over Bridge, Lift & Escalator, Second entry gate | Soft Upgradation-LOA issued on 06.06.2023 COP & PF surface improvement- LOA issued on 17.06.2023 12M wide FOB- LOA issued on 03.10.2023 LOA for Civil Engineering Works in connection of 11 lifts & 15 escalator isssued on 21.07.2023 LOA for Procurement of 11 Lift issued on 06.11.2023 Tender for Procurement of 15 Escalator - financial bid open & under finalization at HQ level | GSU/PA | 90% | 45% | 21.24% | Completed work : 1) Portico -100% 2) Reservation Office 100% 3) PF Surface 100% 4) Ramp work 100% 5) Toilet Block -100% 6) COP & PF Surface 100% 7) SM Room 100% 8) VIP room 100% 9) Toilet Block 100% 10)Parking area 100% 11)Waiting Hall 100% Work in progress : 2) Pathway development 90% 3) Circulating area 85% 4) Compound wall 95% 5) 2nd entry gate 80% 6) Water booth - 85% 7) FOB work- 25% 8) PF-1 Lift 50% 9) PF-1 Escalator- 50% 10) Rear side lift- 65% 11) Rear side escalator- 50% Works yet to be takenup : Seating Facilities in Circulation area | Soft upgradation: 30.06.2025, 06 m FOB: 31.12.2025
2 | Dehu Road | PA | 8.05 | Yes | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works Second entry, Signages | Soft Upgradation-LOA issued on 06.06.2023 COP & PF surface improvement- LOA issued on 17.06.2023 | GSU/PA | 30% | 10% | 8.51% | Completed work : 1. DG Room Work in progress: 1 Downside booking office- 0% 2) Downside circulating area - 0% 3) Downside pf toilet block - 45% 4) Upside booking office - 0% 5)Upside circulating area- 0% 6)COP overall pf 1& 2 -35% Works yet to be takenup : Facade, Portico, Circulating Area, Illumination, renovation, 2nd entry | Soft upgradation: 31.10.2025, 6 m FOB:- 31.03.2026
3 | Akurdi | PA | 33.83 | Yes | Facade, Portico, Circulating Area, Second entry (UP Side), COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Incorporating the local art and culture. Foot Over Bridge, Lift & Escalator, Signage | Soft Upgradation-LOA issued on 06.06.2023 COP & PF surface improvement- LOA issued on 17.06.2023 12M wide FOB- LOA issued on 03.10.2023 LOA for Civil Engineering Works in connection of 11 lifts & 15 escalator isssued on 21.07.2023 LOA for Procurement of 11 Lift issued on 06.11.2023 Tender for Procurement of 15 Escalator - financial bid open & under finalization at HQ level | GSU/PA | 73% | 45% | 39.67% | Completed work : Toilet Block, Waiting area, COP & UGWT (100%) Work in Progress : 1.Water booth completed. Plumbing work balance - 95% 2. Construction of new waiting area with Toilet on LHS -60 % 3. Construction of new waiting area on RHS -60 % 4. Front building - 60 % 5.PCMC Toilet Block - 80 % 6. PF-1 Surfacing - 80 % 7.Boundary Wall- 95 % 8. FOB - 60 % Works yet to be taken up : Illumination & Electrical work | Soft upgradation: 30.09.2025, 12m FOB:31.12.2025
4 | Chinchwad | PA | 20.44 | Yes | Lift & Escalator, Second entry (UP side), Signage, Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Incorporating the local art and culture. Lift & Escalator, Second entry (UP side), Signage, | Soft UpgradationLOA issued on 23.06.2023 COP & PF surface improvement- LOA issued on 17.06.2023 LOA for Civil Engineering Works in connection of 11 lifts & 15 escalator isssued on 21.07.2023 LOA for Procurement of 11 Lift issued on 06.11.2023 Tender for Procurement of 15 Escalator - financial bid open & under finalization at HQ level LOA for Civil Engineering Works in connection of 11 lifts & 15 escalator isssued on 21.07.2023 | GSU/PA | 74% | 42% | 41.58% | Completed work : 1) Construction of New RPF Thana 2) Extension of booking office with provision of OFC room, Electrical panel room, CBS room with toilet. Work in progress : 1) Waiting area (DN Side)- 65% 2) Toilet under FOB- 80% 3) OHE Room -80% 5) Circulating Area and Parking (DN Side) -85% 6) Renovation of Existing Booking office -60% 7) New toilet Block at PF-1/2 - 85% 8) New toilet Block at PF-3/4 -80% 9) Lift 01 and 01 esc. at main entrance - 80% 10) Renovation of water booths and existing toilet -0% 11) Existing waiting room and SS office renovation- 50% 12) Lift 2,3 and 4 - 55% 13) COP Work- 80% 14) Platform surface Improvement- 0% Works yet to be takenup : Illumination | Soft upgradation: 31.08.2025 12m FOB:- Extension 31.03.2026
5 | Hadapsar | PA | 24.86 | Yes | Circulating Area, Provision of new Buildings, FOB, Lift & Escalator, COP, Signage, Illumination, Seating Facilities, Divyangjan Facilities, | Lift & Escalator- LOA issued on 21.07.2023 12M wide FOB- LOA issued on 03.10.2023 | GSU/PA | 71% | 45% | 46.48% | Completed Work : 1. Building A, Building B, Building C, Building D 2. UGWT Work in progress : 1. Over head water tank 2. COP work - 85 (%) Erection completed, 3. Gutter/Drainage Pipe WIP, Sheeting work not started 0% 4. Platform Surface - 40% 5. FOB - 35 % Works yet to be takenup : Facade, Portico, Illumination, Seating Facilities, Signage, Lift & Escalator Sky walk Circulating area Front road | Soft upgradation: 15.12.2025 12m FOB: 15.12.2025
6 | Uruli | PA | 12.86 | Yes | Facade, Portico, Circulating Area, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, COP & PF Surface, Seating Facilities, Signage | Soft Upgradation-LOA issued on 12.07.2023 COP & PF surface improvement- LOA issued on 13.07.2023 | GSU/PA | 94% | 94% | 94.58% | Completed Work : 1. PF Surface 2. COP 3. Toilet Block Work in Progress : 1. VIP Waiting Hall (Painting Balance) 2. Booking Hall (Painting Balance) 3. PF-2 chequered tiles fixing 85(%) 4. Circulating area 70(%) 5. False ceiling work in old station building varandha 90(%) 6. Entrance Gate 80% 7. Seating Facilities 70 % Works yet to be takenup : Illumination | Soft upgradation: 31.03.2026, 12m FOB: - NA
7 | Kedgaon | PA | 12.548 | Yes | Facade, Portico, Circulating Area, Seating Facilities, Illumination, Renovation works, Compound wall.COP & PF Surface, Toilet Block, Divyangjan Facilities, Signage, | Soft Upgradation-LOA issued on 12.07.2023 COP & PF surface improvement- LOA issued on 13.07.2023 | GSU/PA | 100% | 100% | 89.02% | Completed Work : 1. COP 2. Entrance gate 3. Portico 4. Circulating and parking area 5. PF Surface 6. New toilet block 7. Booking office 8. Sitting arrangement 10. Illumination 11. Compound Wall | Soft upgradation and COP work completed on 28.02.2025, 12m FOB: -NA
8 | Baramati | PA | 11.404 | Yes | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Second entry, Signage | Soft Upgradation-LOA issued on 12.07.2023 COP & PF surface improvement- LOA issued on 13.07.2023 | GSU/PA | 75% | 75% | 56.03% | Completed: 1. COP 2.Septic tank 3. New Toilet Block 4. Compound Wall 5. Water booth Work in progress: 1.Construction of Varanda with Lobby 90% 2. Waiting room toilet block work 90% 3. Portico work 85% 4. Platform Surface Kota Stone fixing work 95% 5. Circulating area work 75% 10. Main entrance gate work 70% 11. Booking office renovation work 75% Works yet to be takenup : Seating Facilities | Soft upgradation: 30.06.2025, 12m FOB: -NA
9 | Lonand | PA | 10.478 | Yes | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Toilet Block, Signage | Soft Upgradation-LOA issued on 09.08.2023 COP & PF surface improvement- LOA issued on 11.07.2023 | GSU/PA | 100% | 100% | 88.03% | Completed Work : 1. COP and PF Surface 2. Entrance Hall 3.Construction of Entry Gate 4.Construction of Compound Wall 5.Construction of New portico 6.Construction of Circulation Area 7.Construction of Parking 8.Renovation of Booking Office and Entrance Lobby 9.PF-1 Construction of Waiting Room 10.Seating facilities 11.Illumination | Soft upgradation and COP work completed on 28.02.2025, 12m FOB: -NA
10 | Wathar | PA | 7.974 | Yes | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Second entry | Soft Upgradation-LOA issued on 09.08.2023 COP & PF surface improvement- LOA issued on 11.07.2023 | GSU/PA | 75% | 75% | 68.47% | Completed Work : 1.Union office 2. COP Work in Progress : Construction of Entry Gate 55% Construction of Compound Wall 95% Construction of Parking Area and Circulation Area 80% Renovation of Existing Booking Office and Entrance Lobby 90% Renovation of Portico 90% Improvement of Platform Surface PF1 - 90% Works yet to be takenup : Illumination | Soft upgradation: 30.07.2025 12m FOB: -NA
11 | Satara | PA | 34.313 | Yes | Facade, Portico, Circulating Area, Seating Facilities, Toilet Block, Renovation works, Compound wall, Incorporating the local art and culture, Foot Over Bridge, Lift & Escalator, COP & PF Surface, Divyangjan Facilities, Illumination, Signage | Soft Upgradation-LOA issued on 01.08.2023 COP & PF surface improvement- LOA issued on 11.07.2023 12M wide FOB- LOA issued on 03.10.2023 LOA for Civil Engineering Works in connection of 11 lifts & 15 escalator isssued on 21.07.2023 LOA for Procurement of 11 Lift issued on 06.11.2023 Tender for Procurement of 15 Escalator - financial bid open & under finalization at HQ level | GSU/PA | 75% | 53% | 39.2% | Completed Work : 1.PF-1 Upper class Waiting Room completed. Work in Progress : 1. PF-1 VIP Waiting Room (70%) 2. PF-1 Sation Manager Rest Room (90%) 3. PF-1 Ladies Waiting Room (85%) 4. PF-1 Portico work (90%) 5. PF-1 Main Entry and Exit Gate Work (95%). 6. New Public toilet Work (90%) 7. PF-1 COP work - 90% 6/12 M Wide FOB:- PF-1&2&3&4&5 (60%) Works yet to be takenup : Seating Facilities, Lift & Escalator, Illumination & Signage | Soft upgradation: 30.09.2025 12m FOB: 28.02.2026
12 | Karad | PA | 12.506 | Yes | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Second entry.Signage | Soft Upgradation-LOA issued on 01.08.2023 COP & PF surface improvement- LOA issued on 11.07.2023 | GSU/PA | 64% | 64% | 56.85% | Work Completed:- 1. PF-1 Parking area compound wall Completed 2. PF-1 Upper class Waiting Room Completed Work in Progress : 1. PF-1 Portico work (80%) 2. PF-1 Main Entry Work (50%). 3. Parking area work (90%) 4. Entrance lobby Work (70%) 5. Circuiting Area Work (75%) Works yet to be takenup : Seating Facilities,Illumination & Signage | Soft upgradation: 30.09.2025, 12m FOB: -NA
13 | Sangli | PA | 24.195 | Yes | Facade, Portico, Circulating Area, Lift & Escalator, Toilet Block, Divyangjan Facilities, Illumination, Incorporating the local art and culture.Foot Over Bridge, COP & PF Surface, Seating Facilities, Signage, Renovation works, Compound wall, Second entry | Soft Upgradation-LOA issued on 09.08.2023. COP & PF surface improvement- LOA issued on 09.08.2023. 12M wide FOB- LOA issued on 03.10.2023 | GSU/PA | 70% | 55% | 34.55% | "Completed Work : 1. COP at PF-1 2 New Booking Office Work in Progress : Entry gate -95 % Portico - 90 % Parking area - 60 % Circulation area - 60 % Canopy work for New booking office - 85% Facade - 20 % Second class waiting room - 65 % Upper class waiting room with toilet block - 75% PF surfacing work at PF no.1 - 95 % COP at PF- 2/3 - 30 % FOB- 53 % Compound Wall- 95 % Works yet to be takenup : , Facade, Seating Facilities, Lift & Escalator, Illumination & Signage | Soft upgradation: 30.11.25 12m FOB: 31.03.2026
14 | Hathkalangale | PA | 5.998 | Yes | Facade, Portico, Circulating Area, Seating Facilities, Toilet Block, Illumination, Renovation works, Compound wall, COP & PF Surface, Signage, Divyangjan Facilities | Soft Upgradation-LOA issued on 01.08.2023 COP & PF surface improvement- LOA issued on 09.08.2023. | GSU/PA | 92% | 92% | 87.86% | Completed Work : Construction of Retaining Wall Work in Progress : 1. Improvement of Old Bldg: Not Started 2. Circulating Area & Parking: 80% 3. PF Shelter (COP): 90% 4. PF surfacing: 75% 5. Waiting Hall: 80% 6. Toilet Block: 85% Works yet to be takenup : Seating Facilities, Renovation, Illumination & Signage | Soft upgradation: 21.11.2025 12m FOB: -NA
15 | Kolhapur | PA | 43.031 | Yes | Facade, Circulating Area, COP & PF Surface, Toilet Block, Divyangjan Facilities, Renovation works, Compound wall, Incorporating the local art and culture.Portico & Entrance lobby, Lift & Escalator, Second entry, Seating Facilities, Illumination, Signage, Foot Over Bridge | Soft Upgradation-LOA issued on 01.08.2023 COP & PF surface improvement- LOA issued on 09.08.2023. 12M wide FOB- LOA issued on 03.10.2023 LOA for Civil Engineering Works in connection of 11 lifts & 15 escalator isssued on 21.07.2023 LOA for Procurement of 11 Lift issued on 06.11.2023 Tender for Procurement of 15 Escalator - financial bid open & under finalization at HQ level | GSU/PA | 82% | 48% | 40.56% | Completed Work : 1. AC Waiting Room Work in progress: 1. Improvement of Bldg : 80% 2. Circulating Area & Parking : 15% 3. FOB : 40% 3. PF Shelter (COP): 98% 4. PF surfacing: 100%(Completed as on Instruction) 5. Lift/ Escalator: Not Started 6. Ladies Waiting Room: 80% 7. Toilet Block at PF-1(New) & 2/3: 95% 8. Reservation Room 95% 9. Facade 95% 10.Enty & Exit Gate : 80 % 11. New Portico : 90 % 12. New Booking Office : 95 % 13. Public Toilet : 75 % 13 Illumination 10 % Works yet to be takenup : Seating Facilities, Lift & Escalator & Signage | Soft upgradation: 21.11.2025 12m FOB: 31.03.2025
16 | Phaltan | PA | 0.76 | Yes | Circulating Area, COP & PF Surface, Seating Facilities, Divyangjan Facilities, Illumination, Compound wall | Development of Phaltan Railway Station -LOA issued on 18.09.2023 | GSU/PA | 100% | 100% | 27.32% | Completed Work : COP, PF Surface, Compound Wall, Divyangjan Facilities, Ramp | Soft upgradation and COP work completed on 08.03.2025, 12m FOB: -NA
17 | Kopargaon | PA | 29.939 | Yes | Front Façade improvement, Circulating area improvement, New Parking for 2 & 4 Wheeler & for Divyangjan, New Entry Gate, Provision of boundary wall, Landscaping, Provision of New OH & UG Sump, Drainage improvement, New Water stands with Divyangjan facilities. Improvement to existing station building along with Waiting Halls, Improvement of PF No. 01 (Home) surfacing, Provision of COP on PF No. 01. New 6 m wide FOB with Ramp. Relocation of quarters. Extension and improvement to existing Booking office. New Model toilet, Provision of retiring room. | Soft Upgradation-LOA issued on 15.06.2023 6 M wide FOB- LOA issued on 30.01.2024 | GSU/PA | 75% | 50% | 42.53% | COMPLETED WORK:- Front Façade of Station Building Circulating Area PF Shelter PF Surfacing Waiting Hall Provision of COP on PF - 1 New Parking for 2 & 4 Wheeler New Entry Gate, Provision of boundary wall Landscaping Provision of New OH & UG Sump Improvement to existing station building along with Waiting Halls, Improvement of PF No. 01 (Home) surfacing Relocation of quarters, Extension and improvement to existing Booking office WORK IN PROGRESS:- Toilet (New/ Renovation) 85% Works yet to be takenup : Nil | Soft upgradation: 30.06.25 6 m FOB: - 31.03.26
18 | Belapur | PA | 31.962 | Yes | Front Facade Improvement, Provision of new Portico, Drainage improvement, development of Circulating Area, 2 & 4 wheeler parking, Relocation of sump, Provision of new booking office, relocation of service buildings, PF No. 01 surfacing, Provision of COP, Provision of new model toilet, Improvement to Front Facade. Provision of 6 m wide FOB with Divyangjan facilities. New Water stands with Divyangjan facilities. Provision of new Electrical Sub station. Renovation of existing station building. | Soft Upgradation-LOA issued on 31.07.2023 6 M wide FOB- LOA issued on 13.12.2023 | GSU/PA | 55% | 45% | 33.42% | COMPLETED WORK:- PF Surfacing Waiting Hall (New/ Renovation) PF Shelter Drainage improvement Relocation of sump WORK IN PROGRESS:- New Building/Improvement to Bldg a)Service Building 75% b)Reservation Hall 80% Circulating Area 60% PF Surfacing 25% Toilet (New/ Renovation) 20% 2&4 whelller parking (40%) New elec. sub station (60%) Renovation of existing station building.(20%) Works yet to be takenup : Nil | Soft upgradation:31.12.25 6 m FOB: - 31.03.2026
19 | Daund | PA | 44.1663 | Yes | Drainage improvement, development of Circulating Area and parking on Main entry. Full COP & PF Surface improvement, new toilet Blocks, relocation of existing buildings, water booths, Platform surfacing, repairs and renovation of existing buildings, construction of quarters for relocated occupants | Soft Upgradation-LOA issued on 29.07.2023 6 M wide FOB- LOA issued on 30.01.2024 | GSU/PA | 62% | 62% | 28.49% | COMPLETED WORK:- Station Approach road completed Repairs to existing buildings PF Surfacing WORK IN PROGRESS:- power house area road work in progress 90% PF Shelter (COP) 80% Relocation of Units 80% Improvements to water stands 50% Model Toilet 70% Quarters type-3 80% Works yet to be takenup : Nil | Soft upgradation: 31.12.2025 6 m FOB: - 31.03.2026
20 | Ahmednagar | PA | 30.9202 | Yes | Drainage improvement, Extension of circulating area, Provision of 2 wheeler parking in addition to existing parking. Repairs to COP, PF No. 01 (Home) Surface improvement, Model Toilet with divyangjan facilities, Relocation of existing buildings & offices, water booths, repairs and renovation of existing buildings. New 6 m wide FOB with Ramp adjacent to existing 6 m wide FOB, Provision of new Parcel office.New Water stands with Divyangjan facilities | Soft Upgradation-LOA issued on 31.07.2023 Conversion of 6M to 12 M wide FOB- LOA issued on 30.01.2024 | GSU/PA | 80% | 55% | 46.8% | COMPLETED WORK : Landscaping Divyangjan Toilet Extention of Circulating Area PF Shelter Waiting Hall (New/ Renovation) . Provision of two wheeler parking (200 nos.) Repairs & renovation of existing buildings Improvement to drainage line WORK IN PROGRESS:- New Building/Improvement 85% Works yet to be takenup : Nil | Soft upgradation: 30.07.2025 6 m FOB: - 31.03.2026
Total |  |  | 440.5745

## 3.Status of tec. support ABSS
PCDO for the Month of : April 2025
3. Status of technical support for ABSS
S.No. | Name of Station | Consultant available for techno-economic detailing (Y/N) | Whether PMS/PSSA available (Y/N/Not Required) | Date of NIT for PMS/PSSA Tender opened on 19.06.2023 | TDC/Date for finalization of tenders for PMS/PSSA
1 | Talegaon, Dehu Road, Akurdi, Chinchwad, Hadapsar, Uruli, Kedgaon, Baramati, Lonand, Wathar, Satara, Karad, Sangli, Hatkanangale, Kolhapur, Phaltan | Yes | Y | LOA issued on 21.12.2023 | LOA issued on 21.12.2023
2 | Kopergaon, Belapur, Ahmednagar, Daund | Yes | Y | LOA issued on 21.12.2023 | LOA issued on 21.12.2023
4. Progress of fund utilization under PH-53
S.No. | Division | Budget allocation for the year | Proportionate target for budget utilization till date | Expenditure till date (2025-26) | Expenditure in % proportion of Target | Remarks | Fund required for next year
1 | Pune | 79.19 | Nil | 5.97 | 7.5388 | - | -
Total
5. Progress of appointment of General Consultancy (GC)
S.No. | Name of Project unit | GC required (Y/N) | GC available (Y/N) | NIT date for GC | TDC/Date for finalization of GC | Remarks
1 | CPM/PA | Y | N | - | - | -

## 4. Progress of fund utilization (hidden)
PCDO for the Month of November Year: 2023
4.. Progress of fund utilization under PH-53
S.No. | Division | Budget allocation for the year | Proportionate target for budget utilization till date | Expenditure till date | Expenditure in % proportion of Target | Remarks | Fund required for next year
| Pune | 303.58 | Nil | 3.18 | Nil | - | 121.53
Total

## 5.Progress of appointment of GC (hidden)
PCDO for the Month of : November Year: 2023
5. Progress of appointment of GC
S.No. | Name of Project unit | GC required (Y/N) | GC available (Y/N) | NIT date for GC*5 | TDC/Date for finalization of GC | Remarks
| CPM/PA | Y | N | PSSA DATE | 2023-12-23
Total
*5 To be ommitted if GC is available or not required

## 6 Progress of imp items PH-53.
PCDO for the Month of April 2025
6. Progress of important items of PH-53 (Other than facilities for Divyangian) (Cumulative Progress up to the month of April 2025) (S,T & C - means Scope,Target and Completion for No. of Stations)
S.No. | Item |  | Units | Pune Division | Division Pune
1 | High level Platform (HLPF) | S | Nos | 0
|  | T | Nos | 0
|  | C | Nos | 0
2 | 12m Foot Over Bridge- (FOB) | T | Nos | 5 | 03 GAD (AKRD, HDP,KOP) approved on 06.02.2024 01 GAD of STR is approved on 14.03.2024 01 GAD of SLI is approved on 24.04.2024 01 GAD of TGN is under divisional approval | AKRD, STR, SLI, KOP, HDP
|  | C | Nos | 0
3 | FOB other than 12 m | S | Nos | 6 | - | TGN, DEHR, KPG, ANG, BAP, DD
|  | T | Nos | 0
|  | C | Nos | 0 | -
4 | Ramps | T | Nos | 9 | Uruli, Kedgaon & HTK | URI, KDG, AKRD, HDP, SLI, STR, BAP, KOP, ANG
|  | C | Nos | 2 | Work in progress at URI & KDG | URI,KDG
5 | 2nd Entry | T | Nos | 5 | TGN, DHER, AKRD, CCH & KOP | TGN, DEHR, AKRD, CCH, KOP
|  | C | Nos | 0 | Work in progress atTGN,DEHR,CCH
6 | Ballast less Track (BLT) | T | Nos | 0
|  | C | Nos | 0 | -
7 | Lift | T | Nos | 5 | TGN, CCH, AKRD, STR, KOP | CCH(4), TGN (3), STR(1), SLI (2),KOP (2)
|  | C | Nos | 0 | Work in progress at CCH
8 | Escalator | T | Nos | 8 | TGN, AKRD, CCH, HDP, STR, KOP,SLI | CCH 2, TGN 3, AKRD 2, HDP 2, STR 3, SLI 1, KOP 2, DD 2
|  | C | Nos | 0 | CCH (in progress)
9 | Cover Over Platform (COP) | T | Nos | 20 | TGN, DEHR,AKRD, CCH, HDP, URI, KDG, BRMT, LNN, WTR, STR, KRD, SLI, HTK, KOP & PLLD | All Stations
|  | C | Nos | 9 | Work in progress at all 16 stations | TGN, BRMT, AKRD, LNN, WTR, KDG, KOP, HTK,PHT
10 | Signages (no. of stations) | T | Nos | 20 | TGN, DEHR,AKRD, CCH, HDP, URI, KDG, BRMT, LNN, WTR, STR, KRD, SLI, HTK, KOP & PLLD | All Stations
|  | C | Nos | 2 |  | LNL,KDG

## 7. Facilities for Divyangjan.
PCDO for the Month of : April 2025
7. Facilities for Divyangjan (Cumulative Progress up to the month of April 2025) ( S,T & C - means Scope, Target and Completion. All units in No. of Stations)
Sr.No. | Item |  | Pune
1 | Signage | S | 20 |  |  | All stations
|  | T | 4
|  | C | 2 |  |  | KED, LNN
2 | Standard Ramps | S | 20 | 16 (TGN, DEHR,AKRD, CCH, HDP, URI, KDG, BRMT, LNN, WTR, STR, KRD, SLI, HTK, KOP & PLLD) | TGN, DEHR,AKRD, CCH, HDP, URI, KDG, BRMT, LNN, WTR, STR, KRD, SLI, HTK, KOP & PLLD | All stations
|  | T | 6 | 16
|  | C | 2 | 0 |  | KED, LNN
3 | Parking (Min 2 accessible parking lots) | S | 20 | 8 (URI, KDG, BRMT, STR, KRD, SLI, HTK, KOP) | URI, KDG, BRMT, STR, KRD, SLI, HTK, KOP | All stations
|  | T | 4 | 8
|  | C | 2 | Work in progress at all 8 stations |  | KED, LNN
4 | Ticket Booths | S | 20
|  | T | 4
|  | C | 4 |  |  | HDP, TGN, LNN, KED
5 | Help Booth | S | 0
|  | T | 0
|  | C | 0
6 | Toilet (minimum1) | S | 20 | 15 (TGN, DEHR,AKRD, CCH, HDP, URI, KDG, BRMT, LNN, WTR, STR, KRD, SLI, HTK, KOP) | TGN, DEHR,AKRD, CCH, HDP, URI, KDG, BRMT, LNN, WTR, STR, KRD, SLI, HTK, KOP
|  | T | 6 | 15
|  | C | 5 | In progress at all 15 stations |  | TGN, KDG, URI, LNN, BRMT
7 | Drinking Water Booth | S | 20 | 1 (KOP)
|  | T | 10 | 1
|  | C | 6 | 0 |  | LNN, KDG, PHL, BRMT, SLI, TGN,
8 | Foot over Bridge/ Subway | S | 11 | 3 (STR, SLI, KOP) | STR, SLI, KOP
|  | T | 0 | 3
|  | C | 0 | 0
9 | Elevators | S | 6 | 5 (TGN, CCH, HDP, STR & KOP)
|  | T | 0 | 5
|  | C | 0 | 0

## 11.Strategy of Comm dev at ABSS
PCDO for the Month of April 2025
11.Strategy for Commercial Development at ABSS Stations (All Revenue figures in LakhRs. per annum)
11.A
S.No. | Station Name | Area for Commercial Development in Station Building. Concourse, Platform & Circulation Area, etc. (In Sqm.) | Status of Commercial Development | Revenue Potential per annum | Revenue realized from Commercial Development per annum | Remarks
1 | Talegaon | 13367
2 | Dehu Road | 8752.2
3 | Akurdi | 7778.8
4 | Chinchwad | 14622.7
5 | Hadapsar
6 | Uruli | 8822.5
7 | Kedgaon | 2422
8 | Baramati | 5286.27
9 | Lonand | 10274.58
10 | Wathar | 5824.58
11 | Satara | 11224.11
12 | Karad | 12566.19
13 | Sangli | 13367.91
14 | Hathkalangale | 5860.13
15 | Kolhapur | 21773
16 | Phaltan
17 | Kopargaon | 195.149
18 | Belapur | 50.179
19 | Daund | 554.6107
20 | Ahmednagar | 464.9307
11.B
S.No. | Station Name | Area identified for Commercial development above station building(Airspace) (In Sqm.) | Status of Commercial Development | Revenue potential from Airspace development | Revenue realized from airspace Commercial Development | Remarks
1 | Talegaon, Dehu Road, Akurdi, Chinchwad, Hadapsar, Uruli, Kedgaon, Baramati, Lonand, Wathar, Satara, Karad, Sangli, Hatkanangle, Kolhapur, Phaltan, Kopargaon, Belapur, Daund, Ahmednagar | NIL
11.C
S.No. | Station Name | Land Area Identified for Commercial Development Outside Station Building (A) (in sqm.) | Permissible Built-up area for (A) Considering the complete Masterplan (B) (in sqm.) | Revenue Potential of (B) | Status of Development of (B) | Revenue realized from (B)
1 | Talegaon | 34251.66
2 | Dehu Road | 6486.6
3 | Akurdi | 13633.2
4 | Chinchwad | 5404.45
5 | Hadapsar
6 | Uruli | 2864.96
7 | Kedgaon | 18272.2
8 | Baramati | 71947.03
9 | Lonand | 13903.76
10 | Wathar | 14962.51
11 | Satara | 2225.9
12 | Karad | 16113.09
13 | Sangli | 23362.88
14 | Hathkalangale | 5811.82
15 | Kolhapur
16 | Phaltan
17 | Kopargaon | 0
18 | Belapur | 0
19 | Daund | 3735
20 | Ahmednagar | 765

## 12. Review
12.A Forthnightly Review Meetings at HQ Office
Sr. No. | Dates of Meetings | Remarks
1 | No. of GADs/ GFCs/ Designs/ Approvals pending at start of the month. | Nil
2 | No. of GADs/ GFCs/ Designs/ Approvals pending at end of the month. | Nil
3 | No. of GADs/ GFCs/ Designs/ Approvals pending at more than one month. | Nil
12.B Station Development Review Meeting
Sr. No. | Dates of Meetings | Remarks
1 | 07.01.2025 | With DRM/PA
2 | 26.01.2025 | With CAO( C) RSP
3 | 19.02.2025 | With CAO( C) RSP
4 | 20.02.2025 | With DRM/PA
5 | 24.02.2025 | With DRM/PA
6 | 06.03.2025 | Collector Office Pune
7 | 17.03.2025 | With MI (VC review of Amrit Stations)
8 | 27.03.2025 | With PCOM - PH-16 meeting in DRM Chamber
9 | 31.03.2025 | With DRM/PA
10 | 03,12,18 & 30/04/2025 | HDP station visits
11 | 23.04.2025 | With DRM/PA (LNN, PLLD stations)
12.C Inspection by CE/SDs
Sr.No. | Date of Inspection | Name of Station | Remarks
1 | 13.09.2024 | CCH, TGN, AKRD, DEHR
2 | 27.11.2024 | DD, KDG
3 | 14.12.2024 | HDP
4 | 27.03.2025 | STR, LNN