Station: Talegaon

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | SG3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 40.34 Cr. |
| 6 | Tenders awarded (value and date) | SOFT: (value: 116879776.2 INR, date: 6.6.2023) (Combined tender for TGN, DHRD, AKRD) COP: (value:104599472 INR, date: 17.06.2023) (Combined tender for TGN, DHRD, AKRD, CCH) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combine tender for ABSS Station) FOB:(value:774258585.97 INR, date: 03.10.2023) (Combined tender for TGN, HDP, AKRD, STR, SLI, KOP) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, CP & PF Surface, Toilet Block, Renovation works, Compound wall Incorporating the local art and culture, Seating Facilities, Divyangjan Facilities, Illumination, Signage, Foot Over Bridge, Lift & Escalator, Second entry gate |
| 8 | Progress of work |  |
|  | FOB/Air concourse | FOB – 40 % |
|  | Main Station building | 100 % |
|  | Second entry | 100 %(as per scope in Phase-1) |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100 % |
|  | COP | 100 % |
|  | Lift/Escalators | 62 % |
|  | Circulating area development | 90 % |
| 10 | Physical/Financial progress | Physical Progress - 68% Financial Progress – 57.81 % |
| 11 | TDC | Soft: 28.02.2026, 06 m FOB :31.10.2026, Lift & ESC: 30.11.2026 |
| 12 | Any constraint | NO |

Station: Dehu Road

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | SG-3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 8.05 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 116879776.2 INR, date: 6.6.2023) (Combined tender for TGN, DHRD, AKRD) COP: (value:104599472 INR, date: 17.06.2023) (Combined tender for TGN, DHRD, AKRD, CCH) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works Second entry, Signages |
| 8 | Progress of work |  |
|  | FoB/Air concourse | NA |
|  | Main Station building | 15% |
|  | Second entry | 60% |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | Not Started Yet |
|  | COP | 90 % |
|  | Lift/Escalators | NA |
|  | Circulating area development | UP side -70 % DN side - 80 % |
| 10 | Physical/Financial progress | Physical Progress – 34 % Financial Progress – 28.66 % |
| 11 | TDC | Soft: 31.08.2026 |
| 12 | Any constraint | Existing Booking office to be shifted in order to carry out further works. |

Station: Akurdi

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | SG-3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 33.83 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 116879776.2 INR, date: 6.6.2023) (Combined tender for TGN, DHRD, AKRD) COP: (value:104599472 INR, date: 17.06.2023) (Combined tender for TGN, DHRD, AKRD, CCH) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combine tender for ABSS Station) FOB:(value:774258585.97 INR, date: 03.10.2023) (Combined tender for TGN, HDP, AKRD, STR, SLI, KOP) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, second entry (UP Side), COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Incorporating the local art and culture. Foot Over Bridge, Lift & Escalator, Signage |
| 8 | Progress of work |  |
|  | FOB/Air concourse | FOB - 65.00 % |
|  | Main Station building | 80.00 % |
|  | Second entry | NOT IN SCOPE |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 80.00% |
|  | COP | 85.00 % |
|  | Lift/Escalators | Not Started Yet |
|  | Circulating area development | 85% |
| 10 | Physical/Financial progress | Physical Progress – 73.00 % Financial Progress –65.93% |
| 11 | TDC | Soft: 15.03.2026, 12m FOB: 31.03.2026 Escalator-31.05.26 |
| 12 | Any constraint | NO |

Station: Chinchwad

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | SG-2 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 20.44 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 41823417 INR, date: 26/06/2023) COP: (value:104599472 INR, date: 17.06.2023) (Combined tender for TGN, DHRD, AKRD, CCH) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combined tender for ABSS Station) |
| 7 | Main scope of work | Lift & Escalator, second entry (UP side), Signage, Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Incorporating the local art and culture. Lift & Escalator, Signage, |
| 8 | Progress of work |  |
|  | FOB/Air concourse | Existing FOB Extension - 25.00 % |
|  | Main Station building | 90.00 % |
|  | Second entry | NOT IN SCOPE |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 35.00 % |
|  | COP | 83.00 % |
|  | Lift/Escalators | 55% |
|  | Circulating area development | 90% |
| 10 | Physical/Financial progress | Physical Progress – 77.00 % Financial Progress – 67.56% |
| 11 | TDC | Soft: 15.03.2026, Old FOB Extension :31.08.2026, Lift & ESC: 31.10.2026 |
| 12 | Any constraint | NO |

Station: Uruli

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 12.86 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 131989555.11 INR, date: 12/07/2023) (Combined tender for KDG, ULI, BRMT) COP: (value: 145826595.8 INR, date: 13/07/2023) (Combined tender for KDG, ULI, BRMT) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, COP & PF Surface, Seating Facilities, Signage |
| 8 | Progress of work |  |
|  | FOB/Air concourse | NA |
|  | Main Station building | 80 % |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 80 % |
|  | COP | 70 % |
|  | Lift/Escalators | NA |
|  | Circulating area development | 65 % |
| 10 | Physical/Financial progress | Physical Progress –84 % Financial Progress – 78.46 % |
| 11 | TDC | Soft upgradation: 31.03.2026, 12m FOB: - NA LIFT & ESC: NA |
| 12 | Any constraint | NO |

Station: Kedgaon

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 12.55 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 131989555.11 INR, date: 12/07/2023) (Combined tender for KDG, ULI, BRMT) COP: (value: 145826595.8 INR, date: 13/07/2023) (Combined tender for KDG, ULI, BRMT) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Seating Facilities, Illumination, Renovation works, Compound wall. COP & PF Surface, Toilet Block, Divyangjan Facilities, Signage, |
| 8 | Progress of work |  |
|  | FOB/Air concourse | NA |
|  | Main Station building | 100 % |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100 % |
|  | COP | 100 % |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100 % |
| 10 | Physical/Financial progress | Physical Progress –100% Financial Progress – 99.3 % |
| 11 | TDC | Soft: 28.02.2025, Inaugurated on – 23.05.2025 |
| 12 | Any constraint | NO |

Station: LONAND STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 10.48 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 62172825.95 INR, date: 09/08/2023) (Combined tender for LNND, WTR) COP: (value: 152443795 INR, date: 11.07.2023) (Combined tender for LNND, WTR, STR, KRD) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Divyangjan Facilities, Illumination, Renovation works, Compound wall, Toilet Block, Signage |
| 8 | Progress of work |  |
|  | FoB/Air concourse | NA |
|  | Main Station building | 100% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100% |
|  | COP | 100% |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress -100% Financial progress-99.73% |
| 11 | TDC | Soft upgradation and COP work completed on 28.02.2025, 12m FOB: -NA Station Inaugurated on - 23.05.2025 |
| 12 | Any constraint | NO |

Station: BARAMATI STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 11.40 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 131989555.11 INR, date: 12/07/2023) (Combined tender for KDG, ULI, BRMT) COP: (value: 145826595.8 INR, date: 13/07/2023) (Combined tender for KDG, ULI, BRMT) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall,Signage |
| 8 | Progress of work |  |
|  | FoB/Air concourse | NA |
|  | Main Station building | 100% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100% |
|  | COP | 100% |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress -100% Financial progress-99% |
| 11 | TDC | Soft upgradation & COP: Completed on 30.09.2025 12m FOB: -NA |
| 12 | Any constraint | NO |

Station: Hadapsar

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 47.88 Cr |
| 6 | Tenders awarded (value and date) | SOFT & COP :(value: 118546479 INR, date: 14/03/2023) 12M FOB:(value:774258585.97 INR, date: 03.10.2023) (Combined tender for TGN, HDP, AKRD, STR, SLI, KOP) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combine tender for ABSS Station) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, COP & PF Surface, Toilet Block, Renovation works, Compound wall Incorporating the local art and culture, Seating Facilities, Divyangjan Facilities, Illumination, Signage, Foot Over Bridge, Lift & Escalator, Skywalk connecting to circulating area. |
| 8 | Progress of work |  |
|  | FOB/Air concourse | FOB –100 % |
|  | Main Station building | 100 % |
|  | Second entry | NOT IN SCOPE |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100 % |
|  | COP | 100 % |
|  | Lift/Escalators | 60 % |
|  | Circulating area development | 100 % |
| 10 | Physical/Financial progress | Physical Progress - 98% Financial Progress – 93.41 % |
| 11 | TDC | Soft works, FOB & Skywalk Completed on :10.11.2025, Lift & ESC: 28.02.2026 |
| 12 | Any constraint | NO |

Station: WATHAR STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-6 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 7.97 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 62172825.95 INR, date: 09/08/2023) (Combined tender for LNND, WTR) COP: (value: 152443795 INR, date: 11.07.2023) (Combined tender for LNND, WTR, STR, KRD) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, |
| 8 | Progress of work |  |
|  | FoB/Air concourse | NA |
|  | Main Station building | 100% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100% |
|  | COP | 100% |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress -100% Financial progress-98% |
| 11 | TDC | Soft upgradation & COP: Completed on 30.09.2025 12m FOB: -NA |
| 12 | Any constraint | NO |

Station: SATARA STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-4 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 32.31 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 69411987.21 INR, date: 01/08/23) (Combined tender for STR, KRD) COP: (value: 152443795 INR, date: 11.07.2023) (Combined tender for LNND, WTR, STR, KRD) FOB:(value:774258585.97 INR, date: 03.10.2023) (Combined tender for TGN, HDP, AKRD, STR, SLI, KOP) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combined tender for ABSS Station) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Seating Facilities, Toilet Block, Renovation works, Compound wall, Incorporating the local art and culture, Foot Over Bridge, Lift & Escalator, COP & PF Surface, Divyangjan Facilities, Illumination, Signage |
| 8 | Progress of work |  |
|  | FoB/Air concourse | FOB-55% |
|  | Main Station building | 60% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 52.5% |
|  | COP | 57.5% |
|  | Lift/Escalators | NOT started yet. |
|  | Circulating area development | 20% |
| 10 | Physical/Financial progress | Physical Progress -64% Financial progress - 59.96% |
| 11 | TDC | Soft: 30.09.2026, 12m FOB: 31.05.2026 LIFT & ESC -31.07.2026 |
| 12 | Any constraint | Sanction required for an amount of Rs.19.21 Cr to complete the station in all respect, estimate has been sent for approval but it has been returned from Sr DCM PA stating that there are no fund available. |

Station: KARAD STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 12.51 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 69411987.21 INR, date: 01/08/23) (Combined tender for STR, KRD) COP: (value: 152443795 INR, date: 11.07.2023) (Combined tender for LNND, WTR, STR, KRD) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, COP & PF Surface, Seating Facilities, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall,Signage |
| 8 | Progress of work |  |
|  | FoB/Air concourse | NA |
|  | Main Station building | 100% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100% |
|  | COP | 100% |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress -100% Financial progress-98.81% |
| 11 | TDC | Soft upgradation &COP: Completed on 30.09.2025, 12m FOB: -NA |
| 12 | Any constraint | NO |

Station: SANGLI STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-4 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 24.20 Cr |
| 6 | Tenders awarded (value and date) | SOFT & COP: (value: 48738462.93 INR, date: 09.08.2023) (tender for SLI Station) FOB:(value:774258585.97 INR, date: 03.10.2023) (Combined tender for TGN, HDP, AKRD, STR, SLI, KOP) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combined tender for ABSS Station) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Lift & Escalator, Toilet Block, Divyangjan Facilities, Illumination, Incorporating the local art and culture. Foot Over Bridge, COP & PF Surface, Seating Facilities, Signage, Renovation works, Compound wall. |
| 8 | Progress of work |  |
|  | FOB/Air concourse | FOB- 70 % |
|  | Main Station building | 60% |
|  | Second entry | NOT IN SCOPE |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | NOT started yet |
|  | COP | 60% |
|  | Lift/Escalators | NOT started yet |
|  | Circulating area development | 92% |
| 10 | Physical/Financial progress | Physical Progress -75% Financial progress-69.27% |
| 11 | TDC | Soft: 31.07.26 12m FOB: 31.08.2026 Lift & Escalator – 31.10.2026 |
| 12 | Any constraint | Sanction required for an amount of Rs.14.90 Cr to complete the station in all respect, estimate has been sent for approval but it has been returned from Sr DCM PA stating that there are no fund available. |

Station: HATHKALANGALE STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 5.998 Cr |
| 6 | Tenders awarded (value and date) | SOFT : (value: 66727812.47 INR, date: 01.08.2023) (Combined tender for HTK, KOP) COP : (value: 70808923.5 INR, date: 09.08.2023) (Combined tender for HTK, KOP) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Seating Facilities, Toilet Block, Illumination, Renovation works, Compound wall, COP & PF Surface, Signage, Divyangjan Facilities |
| 8 | Progress of work |  |
|  | FoB/Air concourse | NA |
|  | Main Station building | 70% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 75% |
|  | COP | 90% |
|  | Lift/Escalators | NA |
|  | Circulating area development | 86% |
| 10 | Physical/Financial progress | Physical Progress -79% Financial progress-74.36% |
| 11 | TDC | Soft upgradation: 30.06.2026 12m FOB: -NA |
| 12 | Any constraint | Sanction required for an amount of Rs.10.52 Cr to complete the station in all respect, estimate has been sent for approval but it has been returned from Sr DCM PA stating that there are no fund available. |

Station: KOLHAPUR STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 43.031 Cr |
| 6 | Tenders awarded (value and date) | SOFT : (value: 66727812.47 INR, date: 01.08.2023) (Combined tender for HTK, KOP) COP : (value: 70808923.5 INR, date: 09.08.2023) (Combined tender for HTK, KOP) FOB:(value:774258585.97 INR, date: 03.10.2023) (Combined tender for TGN, HDP, AKRD, STR, SLI, KOP) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combine tender for ABSS Station) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Seating Facilities, Toilet Block, Illumination, Renovation works, Compound wall, COP & PF Surface, Signage, Divyangjan Facilities |
| 8 | Progress of work |  |
|  | FoB/Air concourse | FOB- 47% |
|  | Main Station building | 80% |
|  | Second entry | NOT IN SCOPE |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | NOT started yet |
|  | COP | 98% |
|  | Lift/Escalators | NOT started yet |
|  | Circulating area development | 15% |
| 10 | Physical/Financial progress | Physical Progress -77% Financial progress-70.18% |
| 11 | TDC | Soft : 31.07.2026, 12m FOB: 31.07.2026 LIFT & Escalator – 30.09.2026 |
| 12 | Any constraint | Sanction required for an amount of Rs.12.15 Cr to complete the station in all respect, estimate has been sent for approval but it has been returned from Sr DCM PA stating that there are no fund available. |

Station: Phaltan

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | HG-3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 0.92 Cr |
| 6 | Tenders awarded (value and date) | SOFT: (value: 6200178.66 INR, date: 18/09/2023) |
| 7 | Main scope of work | Facade, Portico, Circulating Area, Toilet Block, Divyangjan Facilities, Illumination, Renovation works, Compound wall, COP & PF Surface, Seating Facilities, Signage |
| 8 | Progress of work |  |
|  | FOB/Air concourse | NA |
|  | Main Station building | 100% |
|  | Second entry | NA |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 100 % |
|  | COP | 100 % |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress –100 % Financial Progress – 99.00 % |
| 11 | TDC | Soft upgradation and COP work completed on 08.03.2025, 12m FOB: -NA |
| 12 | Any constraint | NO |

Station: KOPARGAON STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 29.94 Cr |
| 6 | Tenders awarded (value and date) | SOFT & COP: (value: 67642407.26 INR, date: 15/06/2023) FOB: (value: 967894956.78 INR, date: 30.01.2024) LIFT & ESC: (value: 145329281.63 INR, date: 29/07/2023) |
| 7 | Main scope of work | Front Façade improvement, circulating area improvement, New Parking for 2 & 4-Wheeler & for Divyangjan, New Entry Gate, Provision of boundary wall, Landscaping, Provision of New OH & UG Sump, Drainage improvement, New Water stands with Divyangjan facilities. Improvement to existing station building along with Waiting Halls, Improvement of PF No. 01 (Home) surfacing, Provision of COP on PF No. 01. New 6 m wide FOB with Ramp. Relocation of quarters. Extension and improvement to existing Booking office. New Model toilet, Provision of retiring room. |
| 8 | Progress of work |  |
|  | FOB/Air concourse | GAD approval under progress |
|  | Main Station building | 100% |
|  | Second entry | - |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 80% |
|  | COP | 100% |
|  | Lift/Escalators | Work approval is under process. |
|  | Circulating area development | 70% |
| 10 | Physical/Financial progress | Physical Progress -64.0% Financial progress-59.82% |
| 11 | TDC | Soft : 28.02.2026 6 m FOB: - 31.10.2026 |
| 12 | Any constraint | NO |

Station: BELAPUR STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-5 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 31.96 Cr |
| 6 | Tenders awarded (value and date) | SOFT & COP: (value: 142577810.89 INR, date: 31-07-2023) FOB: (value: 967894956.78 INR, date: 30.01.2024) LIFT & ESC:(value:139376970.91 INR, date: 12.07.2023) (Combined tender for ABSS Stations) |
| 7 | Main scope of work | Front Facade Improvement, Provision of new Portico, Drainage improvement, development of Circulating Area, 2 & 4 wheeler parking, Relocation of sump, Provision of new booking office, relocation of service buildings, PF No. 01 surfacing, Provision of COP, Provision of new model toilet, Improvement to Front Facade. Provision of 6 m wide FOB with Divyangjan facilities. New Water stands with Divyangjan facilities. Provision of new Electrical Sub station. Renovation of existing station building. |
| 8 | Progress of work |  |
|  | FOB/Air concourse | GAD approval under progress |
|  | Main Station building | 80% |
|  | Second entry | - |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 35% |
|  | COP | 100% |
|  | Lift/Escalators | Work approval is under process |
|  | Circulating area development | 70% |
| 10 | Physical/Financial progress | Physical Progress -63.0% Financial progress-58.30% |
| 11 | TDC | Soft: 28.02.2026 ,6 m FOB: - 31.10.2026 Lift & Escalator - 31.12.2026 |
| 12 | Any constraint | NO |

Station: AHMEDNAGAR STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 30.92 Cr |
| 6 | Tenders awarded (value and date) | SOFT & COP :(value: 142577810.89 INR, date: 31-07-2023) (Combined tender for BAP, ANG) FOB: (value: 967894956.78 INR, date: 30.01.2024) LIFTS:(value:139376970.91 INR, date: 12.07.2023) (Combined tender for ABSS Stations) |
| 7 | Main scope of work | Drainage improvement, Extension of circulating area, Provision of 2 wheeler parking in addition to existing parking. Repairs to COP, PF No. 01 (Home) Surface improvement, Model Toilet with divyangjan facilities, Relocation of existing buildings & offices, water booths, repairs and renovation of existing buildings. New 6 m wide FOB with Ramp adjacent to existing 6 m wide FOB, Provision of new Parcel office. New Water stands with Divyangjan facilities |
| 8 | Progress of work |  |
|  | FoB/Air concourse | GAD approval under progress |
|  | Main Station building | 100% |
|  | Second entry | - |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 10% |
|  | COP | 95% |
|  | Lift/Escalators | Work approval is under process |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress -72.0% Financial progress-67.34% |
| 11 | TDC | Soft upgradation: 31.03.2026 6 m FOB: - 31.10.2026 Lift & Escalator - 31.12.2026 |
| 12 | Any constraint | NO |

Station: DAUND STATION

| # | Item | Remarks/details |
| --- | --- | --- |
| 1 | Classification | NSG-3 |
| 2 | Zone | CENTRAL RAILWAY |
| 3 | Division | PUNE |
| 4 | Executing unit | GSU/PA |
| 5 | Sanctioned estimated cost | 42.17 Cr |
| 6 | Tenders awarded (value and date) | SOFT & COP :(value: 198805144.23 INR, date: 29/07/2023) (Combined work for DD,JH,KWV) FOB: (value: 967894956.78 INR, date: 30.01.2024) ESC :(value: 145329281.63 INR, date: 29/07/2023) |
| 7 | Main scope of work | Drainage improvement, development of Circulating Area and parking on Main entry. Full COP & PF Surface improvement, new toilet Blocks, relocation of existing buildings, water booths, Platform surfacing, repairs and renovation of existing buildings, construction of quarters for relocated occupants |
| 8 | Progress of work |  |
|  | FOB/Air concourse | Sr. DCM Pune informed that there is no requirement of FOB. |
|  | Main Station building | 100% |
|  | Second entry | - |
|  | Access control measures | NOT IN SCOPE |
|  | Holding area development | NOT IN SCOPE |
|  | Platform work | 95% |
|  | COP | 75% |
|  | Lift/Escalators | NA |
|  | Circulating area development | 100% |
| 10 | Physical/Financial progress | Physical Progress -54.0% Financial progress-48.24% |
| 11 | TDC | Soft upgradation: 30.09.2026. |
| 12 | Any constraint | NO |